## Sheet1
Project No. (from design column A) | Project Shortname (from bd column C) | Project Name (from design column B) | Stream (from design column D) | Level of building type (from design column E) | (from design column F) | Series | Total Quantity (m2) | (Aug) Total Processed (cumulative) | (Sept) Total Processed (cumulative) | (Oct) Total Process (cumulative) | (Nov) Total Process (cumulative) | (Dec) Total Process (cumulative) | Total Processed | Remarks (Free Form) | Dispatch |  | Outstanding (Integer) |  |  |  | Total Outstanding (Integer) | Closing Date | Order Status (Haven't Start, Pending, On Hold, Completed) | PIC (Dropdown) | Accessories (Remarks) | Holing (Remarks) | (Aug) Not Process (cumulative) | (Sept) Not Process (cumulative) | (Oct) Not Process (cumulative) | (Nov) Not Process (cumulative) | (Dec) Not Process (cumulative) | Total not Processed | Reason (Not Processed)
[15 empty] | Pack | Not Pack | N.Stock | U.Stock | Spec | Make New
25124 | AP24 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | 1 | Tower A | Typical | 1 | 100 | 25 | 25 | 25 | 25 | 25 | 25 |  | 25 | 25 | [10 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50
2
3
[5 empty] | Upper lv.10 | 1
2
|  |  | 2 | Tower B | Typical | 1
2
[5 empty] | Upper lv.10 | 1
2
25124 | AP24 | INDIA - Alekhya Property Developments - Adarsh Parkland Phase 2 Block 4 | 1 | Tower A | Typical | 1
2
3
[5 empty] | Upper lv.10 | 1
2
|  |  | 2 | Tower B | Typical | 1
2
[5 empty] | Upper lv.10 | 1
2
26213 | EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1
2
[5 empty] | Upper lv.10 | 1
2
3
4
[5 empty] | Upper lv.30 | 1
2
26213 | EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1
2
[5 empty] | Upper lv.10 | 1
2
3
4
[5 empty] | Upper lv.30 | 1
2
26213 | EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1
2
[5 empty] | Upper lv.10 | 1
2
3
4
[5 empty] | Upper lv.30 | 1
2
26213 | EG23 | MALAYSIA - C N H Enterprise - EG23, 206 unit DSTH in Elmina City | 1 | Tower A | Typical | 1
2
[5 empty] | Upper lv.10 | 1
2
3
4
[5 empty] | Upper lv.30 | 1
2
26213 | BFD4 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | 1 | Tower A | Typical | 1
2
3
[5 empty] | Upper lv.10 | 1
|  |  | 2 | Tower B | Typical | 1
2
3
26213 | BFD4 | SINGAPORE - Wee Hur Construction - Bedok FD4-4 Blk Apartment | 1 | Tower A | Typical | 1
2
3
[5 empty] | Upper lv.10 | 1
|  |  | 2 | Tower B | Typical | 1
2
3